## Risk Log
Risk Identification and Description |  |  | Risk Assessment
ID | Category | Risk Description & Details | Likelihood | Impact | Strategy and Action Details (including residual risk) | Threshold / trigger current status
RL01 | Example risk 1 | Due to the irregular specifications of the experiment X, the supplied material Y might not meet the requirements leading to work package Z being impossible to complete | Medium | Medium | Prevention: We already planned for a one month test period in the work plan and identified multiple suppliers from where we can get the required material from and choose the best suited for the experiment, limiting the likelihood to low. | Immediate at project start
RL02 | Example risk 2 | Because the productive operation of the plant has priority over our study, there might not be enough live data available to feed our algorithms. | High | High | Mitigation: We use historical data from the plant. This will limit the usefulness of the output since we cannot cover all operational points but the principal proof of concept can still be made. | If after Start + X months we do not have a minimum of Y % of the necessary live data
RL03
Note on A2: An ID that can be used as reference in the project description form
Note on B2: Categories of risks related to the area affected by the risk, e.g.: - Research (e.g. related to goals, content or scope) - Project management (e.g. related to time, budget, personnel) - Exploitation (e.g. related to valorization, IP, legal constraints) ...
Note on C2: A description of the risk that may occur in the project and its causes. What kind of problems will the risk result in and risk dependencies. Formulation guideline: Because of <Condition>, it might be that <Event>, which will lead to <Impact>.
Note on D2: A numeric value denoting the estimate of the probability that the risk will occur. The possible values are: Very high (More than 50 % chance of occuring) High (25 % to 50 % chance of occuring) Medium (10 % to 25 % chance of occuring) Low (5 % to 10 % chance of occuring) Very low (Less than 5 % chance of occuring)
Note on E2: A numeric value denoting the severity of the impact of the risk (should it occur). The possible values are: Very high (E.g. More than 12 months delay, an essential worp package cannot be performed and the main goal of the project cannot be achieved) High Medium (E.g. More than three months delay, A non-essential work package cannot be performed Low Very low (E.g. No measurable impact on time or research content)
Note on F2: Please describe: What is your risk response strategy? The available strategies to deal with the identified risks are: - Avoidance: risk avoidance, working the project or project plan around those conditions or activities which introduce the risk; - Prevention: risk reduction through the proactive implementation of activities to lower the likelihood; - Mitigation: risk reduction though the proactive implementation of activities to lower the impact; - Acceptance: acceptance of the risk. In this cases, contingency plans can also be defined in case the risk occurs; - Transfer/Share: transfer or share a risk with other entities, e.g. through insurances, sub-contracting etc. What are your actions? What is the residual risk in this scenario?
Note on G2: The threshold/trigger at which the planned action is being executed. For follow-up: What is the current status? At what level are we or has the threshold already been reached?